## Legend
Defect Severity
Critical
Major
Moderate
Minor
Cosmetic
Defect Priority
High
Medium
Low
Defect Status
New
Assigned To Developer
Pending Test
Test Failed
Rejected
Cancelled
Closed

## Defects 6_11_2019
Application Component | Defect Type | Defect Priority | Defect Severity | Defect Summary | Steps to Reproduce | Actual Result | Expeced Result | Defect Status | Software Version
Register User | Bug | Medium | Minor | On the user registration screen for 'When is your B'Day', there should be a check on the maximum age limit. Though there is a check on the minimum age limit, but no check available on the maximum age limit. | STEPS: 1) Try registering a new user. 2) On the screen for 'When is your birthday?', try adding the user's B'Day with an invalid YYYY value like 1111 | The system proceeds forward and accepts such a birth year. | The maximum age for the user trying to register should not be more than 50 years old, as already stated on the web page, before start of user registration process. | Assigned To Developer
Register Pad | Bug | Moderate | Minor | While entering the pad id for pad registeration, the check on pad id should not be case sensitive because pad id is an alphaneumeric value | STEPS: 1) On the mobile app, start pad registration. 2) Key in the ID of the pad like test1-pad001A or TEST1-PAD001A | The application does not allow the user to proceed with pad registration. | Since the pad id is a alphaneumeric value, case check should not happen on the same. | Assigned to Developer
Use Pad | Bug | High | Moderate | Observed before 6/11/2019: The 10 hour timer that starts after the first pad use, does not show the updated time when the app is opened after closing. It only shows updated time when the user logs off and logs in. | STEPS: 1) Finish using one pad from the kit. 2) The timer of 10 hours will start in the app. 3) Close the app and try opening after some time. | The timer is stopped when the app is closed and starts back when the app is re-opened. To see the exact time left, the user has to kill the running session of the app and open the new app session by logging in again. | The user should not be required to kill the app session and log in again, for seeing the actual time left to start using the second pad. | Assigned to Developer
Use Pad | Bug | High | Moderate | Observed starting 6/11/2019: The app crashes when the 10 hour timer for starting second pad use, is running and the app is reopened after more than 5 to 7 minutes. | STEPS: 1) Finish using one pad from the kit. 2) The timer of 10 hours will start in the app. 3) Close the app and try opening after 5 to 7 minutes. | The app crashes immediately when tried to open up, while the timer is running internally, for more than 5 to 7 minutes. | The user should not be required to kill the app session and log in again, for seeing the actual time left to start using the second pad. | Assigned to Developer
Use Pad | Bug | Medium | Minor | Since the starting screen says that the pad should not be used for more than 8 hours, hence the pad usage hours option should not be more than 8 | STEPS: 1) Start using the pad and fill the required information. | The application allows you to select more than 8 hours of pad usage. | On the screen for the number of hours for which the pad was used, there should be no option for selecting more than 8 hours, because in the start there is a message stating the same. | Assigned to Developer
Register User | Bug | Medium | Moderate | During User Registration, on the screen for 'Last step - book a phone call!', the first_name, last_name, email id and text reminder phone number appear from cache for the last user that was registered. | STEPS: 1) Start user registration on 'test.qurasense.com'. 2) On the screen for 'Last step - book a phone call!' , observe the values populated for first name, last name and email id. | The values for first name, last name,email id and text reminder phone no are auto populated with the user data for the last user's registration. | The values for first name, last name, email id and text reminder phone no should be auto populated with the data of current user being registered OR Should not be populated at all | Assigned to Developer
Register User | Bug | Medium | Minor | While feeding in the shipping address, the country drop down list should select the desired country based on keyboard input also. | STEPS: 1) Start user registration on 'test.qurasense.com'. 2) On the screen for 'Shipping Address' , try using the keyboard for selecting trhe country, by writing the actual country name and selecting the same. | The country drop down list does not allow selecting the country based on keyboard input. | The user should be able to select the country from the drop down list, based on keyboard input also, if does not want to use the mouse. | Assigned to Developer
Register User | Bug | Low | Major | On the screen for 'Terms, privacy policy and research consent', if you open the privacy policy and click on the hyperlink 'always', the user registration process is terminated abnormally. | STEPS: 1) Start user registration on 'test.qurasense.com'. 2) On the screen for 'Terms, privacy policy and research consent' , open the privacy policy. 3) Scroll down to the section for 'Modification of This Privacy Policy'. 4) There is a hyper link on 'always' 5) Click the hyperlink for 'always' | The user registration process is terminated abnormally and the screen for priacy policy can not be closed. | Either the hyperlink should not be present on 'always' OR The hyperlink should be linked to the right information. | Assigned to Developer
Register Pad | Bug | Medium | Minor | The feature for moving text cursor under magnifying glass on text fields in iOS, should be enabled for all the text fields in the app. | STEPS: 1) Start pad registration on iPhone, using the Qurasense app. 2) On the screen for 'Register your Q-Pads', enter the name of the pad manually. 3) Try editing the first few letters of the pad id, by holding down your finger over the text field, such that the magnifying glass pops up. 4) Even the username text field for logging into the app, should have this feature enabled. | The iOS feature of magnifying glass popping up, for controlling the cursor, for editing text, does not pop up. | The iOS feature of magnifying glass popping up, for controlling the cursor, for editing text, should be added to the app. | Assigned to Developer
Register User | Bug | Low | Cosmetic | The spelling of 'convenient' is incorrect in the Qurasense research trial email. | STEPS: 1) Complete the user registration process and create a new user. 2) There should be a new email out on the user's email id. 3) Under "thank You For registering!', observe the spelling of 'convenient' | The spelling of convenient is written as convinient. | The same should be spelled as 'convenient' | Assigned to Developer
Use Pad | Bug | Low | Cosmetic | When starting to use the pad, the 'Getting Started' screen always comes up to show the guide saying that 'You are the first time user' | STEPS: 1) Log in to the app and use a couple of pads. 2) Log out. 3) Log in again with the same user and register a new pad and start using the same. | The 'Getting Started' screen comes up saying that 'You are the first time user', even though the user is not a first time user. | Either the message on the screen should not say 'first time user' OR The 'Getting Started' screen should not come up for old users. | Assigned to Developer
Use Pad | Enhancement | Medium | Low | The question for 'Which day of the period are you on?' should be asked even while starting to use the second pad of the kit , because the time difference between using first and second pad is not saved anywhere and hence the doctor may not be abl to figure out if the second pad was used on the same day or the next day. | STEPS: 1) Start using of first pad, after registering the pad. 2) Before starting to use the first pad, the system will ask you 'Which day of the period are you on?'. 3) After completing the use of first pad, wait for 10 hours (the max limit) before starting to use the second pad. | Before starting the use of second pad the system does not ask 'Which day of the period are you on?'. | Even for the second pad, the system should ask 'Which day of the period are you on?', because the delay in using the second pad, could change the day of the period as compared to what was feeded during the first pad use. | Assigned to Developer
Logistics Dashboard | Bug | High | Minor | When seraching for a kit on the Logistics_dashboard if the control is on any other page, the control should return to Page 1 after the search results for the kit are retrieved. | STEPS: 1) On the Logistics Dashboard page, click on the three lines in the upper left top corner and click on 'Kits' 2) Browse to any other page apart from page 1. May be try going to Page 5, using the right arrow key at the bottom right of the page. 3) In the top 'Search' section of the dashboard, write the name of the kit that you are looking for. Eg: Test1-001 4) Press the search button. | 1) After the search results are returned, the control still stays on page 5 without any search results there. 2) The page number is displayed as 'Page 5 of 1' | 1) After search results are returned, the control should automatically go to Page 1, where actually the search results are available. 2) The page number displayed at the bottom should always be 'Page 1 of <n>', where <n> is the total number of pages the search results will be diaplayed in. | Assigned To Developer